## Slide 1
LANTERN EDUCATION PARTNERS — SOLUTION PROPOSAL
Every Day Counts
A two-year plan to reduce chronic absenteeism at Riverbend Unified, 2026-27 and 2027-28
Prepared for the Board of Education, September 2026
Illustrative example. Lantern Education Partners and Riverbend Unified are fictional; every price, headcount, date and projected effect here is illustrative.
The problem evidence is real and sourced on the page.
Notes: Thank you for the time. This is a proposal from Lantern Education Partners to reduce chronic absenteeism at Riverbend Unified over the next two school years. Before anything else, one boundary that holds for the whole document. Lantern and Riverbend are illustrative, and every price, headcount, date and projected effect you will see is an illustrative figure, marked as such on the page where it appears. The evidence about the problem itself is real, and each page names the dataset or the report it comes from. If you keep one distinction from today, keep that one.

## Slide 2
THE SITUATION
Contains illustrative figures
Chronically absent without ever being truant
Chronic absenteeism is a count of missed days for any reason — which is why it can be managed like any other operating metric.
18
days
10% of a 180-day school year
0.10 × 180 = 18
HOW IT IS COUNTED
Missing 10 percent or more of school days for any reason — excused, unexcused, or suspension.
Framework for Action: Addressing Chronic Absenteeism through ESSA (ERIC ED617466, 2017)
The federal report-card measure counts 15 days or more; ESSA requires the rate on report cards.
Excused — illness, appointments
Unexcused — no accepted reason
Days out on suspension
All three count the same way
Riverbend's own baseline for 2025-26 is 31% — about 3,100 of 10,000 students. That is the number this proposal moves.
Illustrative district figures
Notes: The measure in front of you is narrower and stranger than most people expect. Chronic absenteeism means missing ten percent or more of school days for any reason at all, which in a one hundred and eighty day year is eighteen days. Excused illness counts. Unexcused days count. Days out on suspension count. That is why a student can be chronically absent and never once be recorded as truant, and it is why this is an operating metric rather than a discipline problem. There is a second counting rule worth knowing: the federal report card measure is fifteen days or more, and the Every Student Succeeds Act requires states to publish the rate. The definition and both counting rules come from the Framework for Action published through ERIC. The Riverbend baseline of thirty one percent, and the three thousand one hundred students behind it, are illustrative figures for this example.

## Slide 3
THE EVIDENCE — PUBLISHED BENCHMARK
The rate is still ten points above 2018-19
It rose by half in the pandemic years and has recovered less than half of that.
20%
25%
30%
35%
40%
45%
2018-19
2019-20
2020-21
2021-22
2022-23
26.4%
24.9%
29.2%
40.2%
36.3%
% of students chronically absent
School year
HOW THIS WAS COMPUTED
A student-weighted city-wide rate: chronically absent students divided by students contributing 10 or more total days, summed across every All Grades school row in that year.
New York City is a published benchmark, not Riverbend's figures.
Source: NYC Open Data — End-of-Year Attendance and Chronic Absenteeism (dataset sgsi-66kk), school years 2018-19 to 2022-23; computed by Lantern.
Notes: The takeaway on this page is that the attendance crisis did not close when buildings reopened. This is New York City, the largest district that publishes this series, used here as a benchmark and not as Riverbend's own numbers. The city ran at twenty six point four percent chronically absent in twenty eighteen nineteen, peaked at forty point two percent in twenty twenty one twenty two, and has come back only to thirty six point three percent. That recovery closes less than half the gap, four years after the disruption began. The method matters for how much weight you put on it. This is a student weighted rate, computed by summing chronically absent students and students contributing ten or more total days across every school row for each year, not by averaging school percentages. The data is the New York City Open Data end of year attendance dataset.

## Slide 4
THE EVIDENCE — DISTRIBUTION
One city, one year: 16% to 46% across districts
Chronic absenteeism concentrates, so a district average is an accounting figure — the plan has to be aimed at the tail.
0%
10%
20%
30%
40%
50%
20
26
24
25
15
30
22
31
3
28
2
21
6
13
29
27
1
11
32
10
17
4
14
18
9
19
12
5
8
7
16
23
% of students chronically absent
Community school district
Lowest: District 20 at 15.5%
Median district: 28.9%
8 of 32 districts sit at or above 35%; 6 sit at or below 20%
Highest: District 23 at 46.2%
The 32 geographic community school districts, All Grades / All Students, 2018-19, as published. District 75, the citywide special-education district, is excluded at 51.5% because its population is not comparable to a geographic district.
Source: NYC Open Data — End-of-Year Attendance and Chronic Absenteeism by District (dataset hags-jh3e).
Notes: The second thing the published data shows is that this problem is not evenly spread, which changes what a plan should target. In one city, in one school year, the thirty two geographic community school districts ran from fifteen point five percent in District twenty to forty six point two percent in District twenty three. The median district sat at twenty eight point nine percent. Eight of the thirty two were at or above thirty five percent while six were at or below twenty percent. A district wide average sitting in the middle of that range is an accounting figure; it describes almost none of the schools inside it. We have excluded District seventy five, the citywide special education district, at fifty one point five percent, because its population is not comparable to a geographic district. Same source, the by district dataset.

## Slide 5
THE EVIDENCE — WHERE IT CONCENTRATES
Two peaks, and one of them is five-year-olds
Absence is worst at the entry to school and at the exit from it.
0%
10%
20%
30%
40%
50%
K
1
2
3
4
5
6
7
8
9
10
11
12
% of students chronically absent
Grade
Kindergarten 45.6%
Grade 5 29.1%
Grade 12 45.2%
WHY BOTH ENDS MATTER
Students chronically absent in both kindergarten and first grade are much less likely to read at grade level by third grade.
Students not reading at grade level by third grade are four times more likely to drop out of high school.
By sixth grade chronic absenteeism is a leading dropout indicator; by high school attendance predicts dropout better than test scores.
Chart source: NYC Open Data — End-of-Year Attendance and Chronic Absenteeism (sgsi-66kk), 2022-23; student-weighted rate per grade, computed by Lantern.
Consequence evidence: Framework for Action: Addressing Chronic Absenteeism through ESSA Implementation (ERIC ED617466, 2017).
Notes: If the plan is going to be aimed somewhere, this page says where. Across the K to twelve span in twenty twenty two twenty three, the rate is worst at both ends: forty five point six percent in kindergarten and forty five point two percent in grade twelve, with the trough at grade five still near twenty nine percent. The kindergarten peak is the one that usually surprises a board, and it is the one with the longest consequences. The Framework for Action reports that students chronically absent in both kindergarten and first grade are much less likely to read at grade level by third grade, and that students not reading at grade level by third grade are four times more likely to drop out. By sixth grade chronic absenteeism is itself a leading dropout indicator, and by high school attendance predicts dropout better than test scores do. So a system that only watches high school is watching one end of a two ended problem.

## Slide 6
WHY STUDENTS MISS SCHOOL
Four kinds of reasons, and only one is refusal
Researchers group the causes as barriers, aversions, disengagement, and myths.
Barriers
Unmanaged asthma, diabetes, mental health and vision problems; transport and housing instability.
Aversions
Bullying, undiagnosed disabilities, and overly punitive discipline.
Disengagement
A negative school climate, or no supportive relationship at school.
Myths
Fears such as lice, and the belief that an excused absence does not count.
Three of the four are conditions a district can change. The EPA estimates 10.5 million school days are lost to asthma each year.
Illustration, not a photograph of any school
Source: Framework for Action: Addressing Chronic Absenteeism through ESSA (ERIC ED617466, 2017); EPA asthma figure cited there.
Notes: Before the recommendation, one page on cause, because it determines what kind of response works. Researchers group the reasons students miss school into four kinds. Barriers are conditions the family cannot simply decide their way past: unmanaged asthma, diabetes, mental health and vision problems, transport and housing instability. The Environmental Protection Agency estimate cited in the same report puts ten and a half million school days lost to asthma alone each year. Aversions are reasons to stay away: bullying, undiagnosed disabilities, overly punitive discipline. Disengagement is a negative school climate or the absence of one supportive relationship. Myths are the beliefs that keep families comfortable with absence, including the idea that an excused day does not count. Only one of those four is anything like refusal, and none of them is solved by a letter home. The illustration beside it is a drawing, not a photograph of any school.

## Slide 7
OUR RECOMMENDATION
Build one attendance system with three tiers
Prevention for everyone, early intervention for the students slipping, and coordinated case support for the students already in crisis.
3
2
1
Rising intensity, fewer students
Tier 3 — Intensive support
Students already chronically absent
Tier 2 — Early intervention
Students approaching the 10% line
Tier 1 — Universal prevention
All students, every day
Lantern designs the system and trains the site leads; Riverbend runs it.
Illustrative staffing: one attendance lead per site, one district coordinator.
The multi-tiered system of supports comes from Framework for Action (ERIC ED617466, 2017).
Notes: Here is what we are proposing. Build one attendance system with three tiers and staff it inside the district. Tier one is universal prevention for every student. Tier two is early intervention for the students who are slipping toward the ten percent line. Tier three is coordinated case support for the students already in crisis. This is not our invention; the Framework for Action identifies a comprehensive multi tiered system of supports, combining prevention with early and consistent interventions, as the most effective response. The division of labour we are proposing is that Lantern designs the system and trains the site leads, and Riverbend runs it. The staffing behind that, one attendance lead per site and one district coordinator, is an illustrative figure at this stage.

## Slide 8
HOW THE SYSTEM WORKS
Contains illustrative figures
Every tier has a trigger, an owner, and a limit
The system escalates on data, not on frustration.
3
2
1
Trigger — already chronically absent, or referred by the attendance team Action — case review, home visit, community partner referral, family attendance plan Owner — district attendance coordinator
Trigger — passes the early-warning threshold in a rolling window Action — same-week family contact, a named adult, a barrier check on health/transport Owner — site attendance lead
Trigger — enrolled Action — attendance expectations, positive messaging, daily data for every teacher Owner — site principal
The boundary: legal action is used only as a very last resort.
England's statutory guidance takes the same shape: schools and local authorities support first, and legal interventions apply only where attendance support does not work, is not engaged with, or is not appropriate.
Sources: Framework for Action (ERIC ED617466, 2017); Department for Education, Working together to improve school attendance, first published 6 May 2022.
Notes: The tiers only mean something if each one has a trigger, an owner and a limit, so here they are. Tier one triggers on enrolment: attendance expectations, positive messaging and daily attendance data in front of every teacher, owned by the site principal. Tier two triggers when a student passes the early warning threshold in a rolling window: same week family contact, a named adult, and a barrier check covering health and transport, owned by the site attendance lead. Tier three triggers when a student is already chronically absent or is referred by the team: case review, a home visit, a community partner referral and an attendance plan agreed with the family, owned by the district attendance coordinator. The thresholds and role titles here are illustrative. The limit is the part I want to be explicit about. The Framework treats legal action as a very last resort, and England's statutory guidance takes the same shape, with legal intervention reserved for cases where attendance support does not work, is not engaged with, or is not appropriate. This system escalates on data, not on frustration.

## Slide 9
DELIVERY PLAN — YEAR ONE
Illustrative dates and scope
Year one ends with a system Riverbend runs itself
Four phases in ten months, each ending in something the board can inspect.
Phase 1
Sep-Nov 2026
Phase 2
Dec 2026-Feb 2027
Phase 3
Mar-May 2027
Phase 4
Jun-Aug 2027
Baseline and root cause
Attendance data audit, barrier survey, site interviews.
DELIVERABLE
Baseline report with a root- cause profile for each site.
Design and build
Early-warning thresholds, the teacher dashboard spec, the family contact playbook.
DELIVERABLE
The attendance operating manual.
Pilot at three schools
Tier 1 and Tier 2 live, with weekly case review.
DELIVERABLE
Pilot results measured against the baseline.
Rollout preparation
Training for every site attendance lead.
DELIVERABLE
Trained attendance leads at every site.
What Riverbend supplies — data access within two weeks of start, a named executive sponsor, released time for the site attendance leads, and family-contact consent under district policy.
Every phase, date and deliverable on this page is illustrative and would be fixed in a statement of work.
Notes: Year one is ten months and four phases, and every phase ends in something you can inspect. Phase one, September to November, is baseline and root cause: an attendance data audit, a barrier survey and site interviews, delivered as a baseline report with a root cause profile for each site. Phase two, December to February, designs and builds the early warning thresholds, the teacher dashboard specification and the family contact playbook, delivered as the attendance operating manual. Phase three, March to May, runs tier one and tier two live at three schools with weekly case review, delivered as pilot results measured against the baseline. Phase four, June to August, trains the attendance lead at every site. What we need from the district is on the same page: data access within two weeks of start, a named executive sponsor, released time for the site leads, and a family contact consent position under district policy. Every date and deliverable on this page is illustrative.

## Slide 10
DELIVERY PLAN — YEAR TWO AND THE GATE
Illustrative dates and scope
In June 2027 the board decides on year two
Year two is district-wide operation and hand-off — and it is conditional.
YEAR ONE — 2026-27
YEAR TWO — 2027-28
1
2
3
4
June 2027
5
6
7
The gate: June 2027
The board reviews pilot results against the baseline and decides to continue, adjust, or stop.
Lantern's year-two fee is not committed until that vote.
No ongoing retainer is proposed after hand-off.
Phase 5 — District-wide operation
Sep-Dec 2027 · all three tiers live, monthly case review
Phase 6 — Tier 3 depth
Jan-Apr 2028 · partner agreements, home-visit protocol
Phase 7 — Hand-off
May-Jun 2028 · Riverbend runs it, Lantern reviews and leaves
Every date, phase and hand-off term on this page is illustrative and would be fixed in a statement of work.
Deliverable on hand-off: a signed operating manual and a trained district attendance team.
Notes: This is the page I would push you to interrogate, because it is where an engagement usually becomes open ended. It does not here. In June twenty twenty seven the board reviews the pilot results against the baseline and decides to continue, adjust or stop, and our year two fee is not committed until that vote. If you continue, phase five runs all three tiers at every site with monthly case review, phase six deepens tier three with partner agreements and a home visit protocol, and phase seven hands the system over, with a signed operating manual and a trained district team. After that we leave. There is no ongoing retainer in this proposal. The dates and terms here are illustrative and would be fixed in a statement of work.

## Slide 11
SCOPE AND BOUNDARY
Illustrative dates and scope
The boundary of what we are proposing
Nine deliverables, each included, optional at extra cost, or out of scope.
Deliverable
Year one
Year two
Attendance data audit
Included
Included
Root-cause barrier survey
Included
Not included
Early-warning threshold design
Included
Included
Teacher dashboard specification
Included
Included
Family contact playbook
Included
Included
Site attendance lead training
Included
Included
Home-visit protocol
Optional
Included
Community partner agreements
Optional
Included
Student information system integration build
Not included
Not included
Included
Optional at additional cost
Not included
WHAT ONLY RIVERBEND CAN SUPPLY
Data access within two weeks
A named executive sponsor
Released time for site leads
Family-contact consent policy
Not included: the student information system integration build is a district IT procurement.
Scope shown is illustrative.
Notes: Proposals are usually vague at exactly the point where they should be precise, so this page states the boundary. Nine deliverables, each marked included in a given year, optional at additional cost, or not included, with the status written as a word in the cell so it survives being printed or forwarded in black and white. The home visit protocol and the community partner agreements are optional in year one and included in year two. The student information system integration build is not included at all, because that is a district information technology procurement and pricing it here would be pretending to a control we do not have. Four things only Riverbend can supply are listed beside the grid: data access within two weeks, a named executive sponsor, released time for site leads, and a family contact consent policy. The scope shown is illustrative and would be fixed in a statement of work.

## Slide 12
COMMERCIAL TERMS
All amounts are illustrative
$312,000 over two years, year two conditional
Fixed fee by phase, payable on deliverable acceptance.
Line item
Amount (USD)
Year one — 2026-27
Phase 1 · Baseline and root cause
$42,000
Phase 2 · Design and build
$68,000
Phase 3 · Pilot at three schools
$54,000
Phase 4 · Rollout preparation
$38,000
Year one subtotal
$202,000
Year two — 2027-28, conditional on the gate
Phase 5 · District-wide operation
$52,000
Phase 6 · Tier 3 depth
$34,000
Phase 7 · Hand-off
$24,000
Year two subtotal
$110,000
Total, two school years
$312,000
$312,000
total across two school years
PRICE BASIS AND TERMS
Fixed fee per phase, inclusive of travel and exclusive of software licences.
Payable on written acceptance of each phase deliverable.
Quotation valid for 90 days.
Every amount, subtotal, total and payment term on this page is illustrative and would be fixed in a signed statement of work.
The year-two subtotal of $110,000 is released only by the June 2027 board vote; no ongoing retainer is proposed.
Notes: The number is three hundred and twelve thousand dollars across two school years, and it is broken out so you can see what each part buys. Year one is two hundred and two thousand across the four phases. Year two is one hundred and ten thousand across the three remaining phases, and that half is released only by the June twenty twenty seven vote we just discussed. The basis is a fixed fee per phase, inclusive of travel and exclusive of any software licence the district chooses to buy, payable on written acceptance of each phase deliverable rather than on elapsed time. The quotation would be valid for ninety days from the proposal date. Every amount and term on this page is illustrative for this example.

## Slide 13
PROJECTED EFFECT
Modeled, not measured
A modeled nine-point reduction
The projection is a model, not a measurement — and it fails first at staffing.
2025-26
Tier 1
Tier 2
Tier 3
June 2028
Baseline 31.0%
Tier 1 −2.5
Tier 2 −4.0
Tier 3 −2.5
Projected 22.0%
ASSUMPTIONS THIS MODEL RESTS ON
Attendance data access from month one
One trained attendance lead at every site
Family contact in the same week of a Tier 2 trigger
No change to the school calendar or bell schedule
WHERE IT FAILS FIRST
Site staff time is not released — the gate holds rollout until leads are named · executive sponsor
Data access slips past month one — the baseline narrows to the four largest sites · data lead
Tier 3 partner capacity is short — agreements move to Phase 2, Tier 3 stays at pilot sites · Lantern
Modeled and illustrative, not measured. These values are not derived from the NYC benchmark series shown earlier.
Notes: I want to be careful with this page, because it is the one most likely to be quoted back without its qualifiers. This is a model, not a measurement. It starts from the illustrative thirty one percent baseline and shows a modeled contribution from each tier, two and a half points from universal prevention, four points from early intervention and two and a half points from intensive support, reaching a modeled twenty two percent by June twenty twenty eight. None of it is derived from the New York City series we showed earlier. It rests on four assumptions that are worth testing: data access from month one, one trained attendance lead released at every site, family contact in the same week of a tier two trigger, and no change to the calendar or bell schedule. It fails first at staffing, and the response to that is the phase gate itself, which holds rollout until leads are named. If data access slips, the baseline narrows to the four largest sites. If partner capacity is short, tier three stays at the pilot sites while agreements catch up.

## Slide 14
THE NEXT STEP
One vote, on 8 October 2026
Approve Phase 1 and name the executive sponsor at the October meeting.
THE ASK
The board approves Phase 1 funding and names the executive sponsor.
Regular meeting, 8 October 2026.
The superintendent brings the item; the board votes.
Within two weeks of the vote, the data access request is issued.
In November, the baseline report is delivered.
Before then, we need one named data contact from the district.
Lantern Education Partners and Riverbend Unified are fictional; the client, prices, dates and projections in this deck are illustrative. The problem evidence is real and sourced where it appears.
SOURCES USED IN THIS DECK
ERIC ED617466 — Framework for Action
NYC Open Data — attendance (sgsi-66kk)
NYC Open Data — by district (hags-jh3e)
DfE — Working together to improve attendance
Notes: What we are asking for today is one vote. At the regular meeting on the eighth of October the board approves phase one funding and names the executive sponsor, with the superintendent bringing the item. Within two weeks of that vote we issue the data access request, and in November you receive the baseline report. Before then we need one named data contact from the district, and that is the whole ask. Every source used in this deck is linked on this page, so anything you heard today about the size or shape of the problem can be checked directly. As on the cover, Lantern Education Partners and Riverbend Unified are illustrative, and the client, prices, dates and projections in this document are illustrative; the problem evidence is real and sourced where it appears.